## Overview
AUTOSAR CAN Driver - SRS Rewrite Training Assignment
Item | Description |  | Workflow
Assignment purpose | Rewrite a project-level SRS for the AUTOSAR CAN Driver based on AUTOSAR_SWS_CANDriver. |  | Step 1 | Study SWS | Step 2 | Draft SRS | Step 3
Target module | CAN Driver only. Excludes CanIf, CanSM, CanTp and CAN Transceiver. |  | Identify applicable SWS requirements | Classify function/configuration/error requirements | Rewrite in project SRS format | Add source ID and verification method | Cross-review
Training model | Two teams work in parallel, then perform cross-review and merge into one baseline package. |  | Step 4 | Resolve findings | Step 5 | Merge and baseline
Primary input | AUTOSAR_CP_SWS_CANDriver, project SRS template, CAN Driver configuration and available source code. |  | Correct gaps, duplicates and ambiguity | Lead consolidates both teams | Release SRS and traceability package
Main outputs | CAN Driver SRS, SWS-SRS traceability matrix, assumptions/open points and review log.
Requirement style | Atomic, testable shall-statement with actor, trigger/condition, expected behavior and trace source.
Planned duration | 5 working days
Team size | 10 trainees, 5 members per team. Replace placeholder names before assignment.
Classification | Internal Use
Reference guidance
Official reference | AUTOSAR Classic Platform R24-11 - Specification of CAN Driver | https://www.autosar.org/fileadmin/standards/R24-11/CP/AUTOSAR_CP_SWS_CANDriver.pdf
Internal reference | 06_Autosar_Communication_Modules_CAN.pptx | Use internal material for architecture/context; use AUTOSAR SWS IDs as the requirement source.
Note | If the project uses another AUTOSAR release, retain that release consistently in all SRS and traceability entries.

## Open point
OP ID | Sub-ID | Related SRS / SWS ID | Description (gap, ambiguity, assumption) | Type | Raised by | Proposed resolution | Status
OP-01 | B05b | SWS_Can_xxxxx | (example) R24-11 defines no runtime error for X – confirm with mentor | Open point | Member 9 | Ask mentor; if none, mark Not applicable | Open
OP-B01b-01 | B01b | SWS_Can_00226; SWS_Can_00108; CAN_SRS_B151 | CONFLICT: SWS_Can_00226 Description says polling occurs when CAN_RX_PROCESSING is set to POLLING [p.82]; SWS_Can_00108 says POLLING or MIXED [p.82]. Both are in the same SWS release R24-11. | Ambiguity | MinhNV110 | Confirm with mentor which statement governs. CAN_SRS_B151 stays CONFLICT until decided. | Open
OP-B01b-02 | B01b | Slide 40 vs SWS_Can_00226/00108 | CONFLICT: Slide 40 (Autosar_Communication_Module_CAN.pptx, release not stated) describes Can_MainFunction_Read as polling of TX confirmation when CAN_TX_PROCESSING is POLLING; SWS_Can_00226/00108 [p.82] say RX indications / CanRxProcessing. Slides are supporting only; SRS follows the SWS. | Ambiguity | MinhNV110 | Confirm with mentor and correct the slide. | Open
OP-B01b-03 | B01b | CAN_SRS_B152; Rx sequence (polling) | GAP: Slide 42 refers to '9.9 Receive indication (polling mode)'. SWS R24-11 chapter 9 has only 9.1 and 9.2, and 9.1 refers to the CanIf specification for Rx sequence diagrams [p.87]; the CanIf SWS was not provided. Diagram content on slides 41–42 is not available in extracted text — manual verification required. The Rx sequence (polling) therefore covers only the CAN Driver side. | Gap | MinhNV110 | Provide the CanIf SWS (same release) or confirm the CAN Driver-only sequence. | Open
OP-B01b-04 | B01b | SWS_Can_00279; 00396; 00012; 00395; 00423; 00060; 00501; 00299; 00300; 00489; 00490 | BOUNDARY: These Rx items are shared with, or not clearly assigned between, B01a (interrupt, HRH, ID/DLC/payload) and B01b (polling); SWS_Can_00395 (CAN_E_DATALOST) belongs to B05b per Task assignment. They are not in the B01b Traceability sheet. Task assignment requires boundaries to be agreed first. Text on p.46 (callbacks implemented as if call context was ISR) has no requirement ID and was not converted. | Open point | MinhNV110 | Agree split with Member 1 (B01a) and mentor. | Open
OP-B01b-05 | B01b | CAN_SRS_B150–B155 | GAP: The SWS does not define verification methods. Methods used here (Unit Test, Static Analysis, Code Review) come from the vocabulary in the peer example rows (B100, B400-B563); assigning each to a requirement is a proposal, not a source statement. | Gap | MinhNV110 | Mentor to define allowed verification methods. | Open
OP-B01b-06 | B01b | SWS_Can_00180; SWS_Can_00007; CAN_SRS_B155 | GAP: SWS_Can_00180 permits an empty define when no polling is used (kept in Traceability as Not covered); SWS_Can_00007 (complete polling) concerns all event types and is not in the B01b Traceability sheet. Treatment not specified. | Gap | MinhNV110 | Confirm with mentor whether to add rows or keep as traceability-only. | Open
OP-B01b-07 | B01b | CAN_SRS_B150; B151; B152 | GAP: Not specified in the provided sources: how a received L-PDU is detected during polling (hardware-specific), preconditions such as Can_Init / controller state for Can_MainFunction_Read, caller of Can_MainFunction_Read beyond 'Available via SchM_Can.h', CanMainFunctionPeriod value, and any DET check for Can_MainFunction_Read (none found in reviewed sections — manual verification required). | Gap | MinhNV110 | Obtain hardware/project configuration and confirm with mentor. | Open
OP-B01b-08 | B01b | Template sheets | INCONSISTENCY: (a) Template example row of Traceability has one more value than its headers (peer rows B400+ follow the headers; headers were followed); (b) Assignment Matrix uses 'Member B1' while Task assignment uses 'Member 2' for B01b; (c) Boundary rules say 'Member 8 (B05a) owns all DET rows' but Task assignment lists B05a = Member 7 and B05b = Member 8; (d) boundary rules mention 'M8-M9' while only 8 members are listed. Owner = account name from Task assignment (as in peer rows). | Open point | MinhNV110 | Mentor to confirm numbering and Traceability column layout. | Open
OP-B01b-09 | B01b | Source identity | GAP: Slides state no AUTOSAR release (slide 23 cites 'AUTOSAR_SWS_CANDriver' only), and the Overview names '06_Autosar_Communication_Modules_CAN.pptx' while the uploaded file is 'Autosar_Communication_Module_CAN.pptx'. SWS release R24-11 is consistent between the PDF metadata/header and the Overview. | Gap | MinhNV110 | Confirm the slide file identity. | Open
OP-B01b-10 | B01b | ECUC_Can_00438; 00490; 00437; 00484 | CITATION: Page numbers were taken from the PDF text layer (physical page = printed 'n of 159'). Configuration classes of CanMainFunctionRWPeriodRef and CanHardwareObjectUsesPolling not fully verified — manual verification required. ECUC_Can_* IDs are cited in the SRS Template only, not listed in Traceability. | Open point | MinhNV110 | Human check against the PDF. | Open
OP-B03-01 | B03 | CAN_SRS_B300; SWS_Can_00361 | SWS_Can_00361 does not state which wakeup source ID is passed to EcuM_SetWakeupEvent. Assumption: the source referenced by CanWakeupSourceRef (ECUC_Can_00359), same as SWS_Can_00364. | Assumption | HuyPB2 | Confirm with mentor | Open
OP-B03-02 | B03 | CAN_SRS_B301; SWS_Can_00360 | Return value of Can_CheckWakeup is defined as 'API call accepted / not accepted', not 'wakeup detected / not detected'. SRS keeps the SWS meaning; wakeup result is only visible via EcuM_SetWakeupEvent. | Ambiguity | HuyPB2 | Confirm with mentor | Open
OP-B03-03 | B03 / B05b | SWS_Can_00369; SWS_Can_00370; SWS_Can_00373 | These requirements name Can_MainFunction_Wakeup for polling of controller mode transitions, but §8.5.1.5 assigns this to Can_MainFunction_Mode. Treated as SWS text defect. | Gap | HuyPB2 | Handled by B05b under Can_MainFunction_Mode; no B03 row | Open
OP-B03-04 | B03 | ECUC_Can_00330 (CanWakeupSupport) | No SWS shall-requirement defines driver behavior when CanWakeupSupport = FALSE. No SRS row created; used only as precondition in B302/B304. | Gap | HuyPB2 | Ask mentor; if none, keep as precondition only | Open
OP-B03-05 | B03 / A03 | CAN_SRS_B305; SWS_Can_00270; SWS_Can_00048 | Boundary with A03: SLEEP-related transitions (SWS_Can_00257, 00258, 00265, 00266, 00267, 00290, 00294, 00404, 00405) and SWS_Can_00048 stay with A03 (Can_SetControllerMode). B03 covers only the hardware-wakeup transition SLEEP -> STOPPED. | Assumption | HuyPB2 | Agree with A03 (HuyTNG, KhoaHD10) during cross-review | Open
OP-B03-06 | B03 | CAN_SRS_B307; CAN_SRS_B308; SWS_Can_00445..00447 | ICU notification applies only to external CAN controllers. If the target uses on-chip controllers only, B307/B308 become Not applicable. | Open point | HuyPB2 | Confirm target hardware with mentor | Open
OP-B03-07 | B03 | CAN_SRS_B300; CAN_SRS_B302; CAN_SRS_B304 | Wakeup reporting calls EcuM directly (EcuM_CheckWakeup, EcuM_SetWakeupEvent), while Team Standard 3.4 says requirements stop at the call to CanIf. SWS mandates these EcuM calls (§7.7, §8.6.2), so they are kept. | Assumption | HuyPB2 | Confirm exception to boundary rule with B00 / mentor | Open
OP-B03-08 | B03 | CAN_SRS_B307; CAN_SRS_B308 | The CAN Driver configuration has no parameter for the ICU channel used for wakeup. Assumption: the mapping comes from the project / ICU configuration. | Assumption | HuyPB2 | Confirm with mentor together with OP-B03-06 | Open
OP-B03-09 | B03 / A01 | CAN_SRS_B310; SWS_Can_00602 | (1) Trigger 'Can_Init' for programming the selective wakeup filter falls in A01 scope. (2) SWS does not explicitly state that non-matching frames shall not wake the controller; kept as assumption. | Assumption | HuyPB2 | Agree Can_Init trigger with A01; confirm (2) with mentor | Open
OP-B03-10 | B03 / B05a | CAN_SRS_B311; CAN_SRS_B312 | B05a deferred the Can_CheckWakeup DET checks (OP-B05a-13). B03 now owns them as B311/B312. B05a DET Matrix should link to these rows. | Open point | HuyPB2 | Inform ChinhDNT; B05a updates DET Matrix links | Open
OP-B02-01 | B02 | All | Use AUTOSAR CP R24-11 as the source release. The available attached PDF is R25-11; source IDs and wording still need verification against R24-11. | Assumption | MinhPT44 | Author / reviewer: verify in SWS R24-11. | Open
OP-B02-02 | B02 | CAN_SRS_B02_01 | Check whether SWS R24-11 defines Can_MainFunction_BusOff behaviour before Can_Init. Do not add a guessed reaction. | Open point | MinhPT44 | Author / CAN-B05: verify in SWS R24-11. | Open
OP-B02-03 | B02 | CAN_SRS_B02_07 | Check the specified error-state result while STOPPED after bus-off and before restart. Do not assign a result without source evidence. | Open point | MinhPT44 | Author / reviewer: verify in SWS R24-11. | Open
OP-B02-04 | B02 | CAN_SRS_B02_07 | Check invalid-input behaviour when CanDevErrorDetect = FALSE. Do not extrapolate DET-enabled behaviour. | Assumption | MinhPT44 | Author / CAN-B05: verify in SWS R24-11. | Open
OP-B05a-02 | B05a | CAN_SRS_B500 | CAN SWS does not define the ModuleId value or the Det_ReportError prototype (Det_ReportError only listed in §8.6.2). InstanceId = CanIndex (ECUC_Can_00320). | Assumption | ChinhDNT | Take ModuleId from AUTOSAR BSW Module List; confirm with mentor | Open
OP-B05a-05 | B05a | Task assignment | Task assignment lists B05a as Member 7; Team Standard 3.4 says "Member 8 (B05a) owns all DET rows". | Open point | ChinhDNT | Confirmed owner with team lead and fixed the assignment | Closed
OP-B05a-06 | B05a | SWS_Can_91019 | CAN_E_INIT_FAILED (0x09) is defined but no API requirement in R24-11 raises it. | Gap | ChinhDNT | No SRS row; Not applicable | Open
OP-B05a-09 | B05a | §8.5 | No DET check is specified for Can_MainFunction_Write/Read/BusOff/Wakeup/Mode. | Gap | ChinhDNT | No SRS row; Not applicable | Open
OP-B05a-10 | B05a | CAN_SRS_B505 | SWS says "out of range" for Controller without a numeric definition. | Assumption | ChinhDNT | Controller invalid if >= number of configured CanController. Align with B04a/B04b | Open
OP-B05a-11 | B05a | SWS_Can_00218, SWS_Can_00505 | These require E_NOT_OK also when DET is off; B05a covers only the DET report. | Assumption | ChinhDNT | B05b owns the non-DET E_NOT_OK behaviour | Open
OP-B05a-12 | B05a | CAN_SRS_B504 | §7.3.5 defines invalid transitions only for CAN_CS_STARTED and CAN_CS_SLEEP; nothing for CAN_CS_STOPPED or an out-of-range Transition value. | Ambiguity | ChinhDNT | Ask mentor | Open
OP-B05a-13 | B05a | DET Matrix (Deferred) | Budget: 9 SRS. Scope: Can_Write, Can_SetControllerMode, Can_Init, Can_DeInit (17 SWS IDs). Can_SetBaudrate DET checks (SWS_Can_00492, 00493, 00494) are covered by B04a. Deferred - Low: Can_GetVersionInfo (00177); Can_Disable/EnableControllerInterrupts (00205, 00206, 00209, 00210); Can_CheckWakeup (00362, 00363); Can_GetControllerErrorState/Mode/Rx/TxErrorCounter (91005-91007, 91016-91018, 00512-00514, 00517-00519); timestamp APIs, SWS DRAFT (00521-00523, 00525, 00526, 00529-00532, 00535-00537). Generic: SWS_Can_00026 (umbrella statement) and SWS_Can_00089 (E_NOT_OK stated explicitly in every in-scope Std_ReturnType source ID). | Assumption | ChinhDNT | Agree scope with reviewer; next candidates if budget grows: Can_CheckWakeup, Can_Disable/EnableControllerInterrupts | Open
OP-B05a-14 | B04a / B05a | SWS_Can_00492, 00493, 00494; CAN_SRS_401-B403 | B04a rows CAN_SRS_401-403 and B05a rows both traced the Can_SetBaudrate DET requirements (CHK-10 duplicate). | Open point | ChinhDNT | Cross-review decision: B04a keeps SWS_Can_00492/00493/00494 (CAN_SRS_401-403); removed from B05a SRS and Traceability | Closed
OP-B05a-15 | B05a | CAN_SRS_B500 | SWS does not define the check order when several development errors apply to one call; with SWS_Can_00091 only the first one is reported. | Assumption | ChinhDNT | Order: CAN_E_UNINIT -> Controller/Hth -> other parameters -> state transition. Confirm with mentor | Open
OP-B01a-01 | B01a | CAN_SRS_B100; SWS_Can_00396 | Confirm that the relevant receive hardware objects are configured for interrupt processing. | Open point | SonDD15 | Confirm CanRxProcessing and CanHardwareObjectUsesPolling in the project CAN configuration. | Open
OP-B01a-02 | B01a | CAN_SRS_B101; SWS_Can_00420 | Confirm whether the selected CAN hardware resets the RX interrupt flag automatically. | Open point | SonDD15 | Confirm the RX interrupt-flag reset behavior from the selected CAN hardware information. | Open
OP-B01a-03 | B01a | CAN_SRS_B102; SWS_Can_00279 | Confirm the configured mapping from receive hardware objects to Hoh and abstract CanIf ControllerId. | Open point | SonDD15 | Confirm the receive Hardware Object, Hoh and abstract CanIf ControllerId mapping in the project configuration. | Open
OP-B01a-04 | B01a | CAN_SRS_B103; SWS_Can_00423 | Confirm which configured HRHs accept Extended CAN identifiers. | Open point | SonDD15 | Confirm the identifier type configured for each relevant HRH. | Open
OP-B01a-05 | B01a | CAN_SRS_B104; CAN_SRS_B105; SWS_Can_00501; SWS_Can_00416; SWS_Can_00060 | Confirm whether CAN FD reception is enabled in the project configuration. | Open point | SonDD15 | Confirm CAN FD reception support and the applicable CAN FD configuration. | Open
OP-B01a-06 | B01a | CAN_SRS_B105; SWS_Can_00060 | Confirm whether the CAN hardware receive-buffer representation matches the AUTOSAR byte-array representation or requires an adapted SDU buffer. | Open point | SonDD15 | Confirm the receive-buffer representation of the selected CAN hardware. | Open
OP-B04b-01 | B04b | CAN_SRS_B451 - B454 | Configuration settings (baudrate, timing, FD) have only ECUC_Can IDs in the PDF, no SWS_Can ID. I used the ECUC IDs. | Ambiguity | NamHV26 | Ask mentor: is an ECUC_Can ID accepted as source ID? | Open
OP-B04b-02 | B04b | CAN_SRS_B451 | SWS does not say directly that Can_Init uses the default baudrate. I derived it from SWS_Can_00245 and ECUC_Can_00435. | Assumption | NamHV26 | Confirm in cross-review. | Open
OP-B04b-03 | B04b | CAN_SRS_B455 | Error CAN_E_INIT_FAILED exists in the error table, but no requirement says when it is raised. | Gap | NamHV26 | Pass to ChinhDNT (B05a, owns DET errors). | Open

## DET Matrix
DET error matrix - AUTOSAR CP R24-11 SWS CAN Driver (DET development errors for all APIs)
API | Service ID (ApiID) | CAN_E_PARAM_POINTER (0x01) | CAN_E_PARAM_HANDLE (0x02) | CAN_E_PARAM_DATA_LENGTH (0x03) | CAN_E_PARAM_CONTROLLER (0x04) | CAN_E_UNINIT (0x05) | CAN_E_TRANSITION (0x06) | CAN_E_PARAM_BAUDRATE (0x07) | CAN_E_INIT_FAILED (0x09) | CAN_E_PARAM_LPDU (0x0A) | Return on DET error | Extra config condition | SRS IDs (CAN_SRS_) | Status
Can_Init | 0x00 | [5 empty] | SWS_Can_00174 SWS_Can_00408 |  |  |  | None (void) |  | 500; 502 | In scope - Medium
Can_GetVersionInfo | 0x07 | SWS_Can_00177 | [8 empty] | None (void) | CanVersionInfoApi | - | Deferred - Low (OP-B05a-13)
Can_DeInit | 0x10 | [5 empty] | SWS_Can_91011 SWS_Can_91012 |  |  |  | None (void) |  | 500; 503 | In scope - Medium
Can_SetBaudrate | 0x0F |  |  |  | SWS_Can_00494 | SWS_Can_00492 |  | SWS_Can_00493 |  |  | E_NOT_OK | CanSetBaudrateApi | 401; 402; 403 (B04a) | Covered by B04a (OP-B05a-14)
Can_SetControllerMode | 0x03 |  |  |  | SWS_Can_00199 | SWS_Can_00198 | SWS_Can_00200 (00409, 00411) |  |  |  | E_NOT_OK |  | 500; 501; 504; 505 | In scope - Critical
Can_DisableControllerInterrupts | 0x04 |  |  |  | SWS_Can_00206 | SWS_Can_00205 |  |  |  |  | None (void) |  | - | Deferred - Low (OP-B05a-13)
Can_EnableControllerInterrupts | 0x05 |  |  |  | SWS_Can_00210 | SWS_Can_00209 |  |  |  |  | None (void) |  | - | Deferred - Low (OP-B05a-13)
Can_CheckWakeup | 0x0B |  |  |  | SWS_Can_00363 | SWS_Can_00362 |  |  |  |  | E_NOT_OK (00089) |  | - | Deferred - Low (OP-B05a-13)
Can_GetControllerErrorState | 0x11 | SWS_Can_91007 |  |  | SWS_Can_91006 | SWS_Can_91005 |  |  |  |  | E_NOT_OK |  | - | Deferred - Low (OP-B05a-13)
Can_GetControllerMode | 0x12 | SWS_Can_91018 |  |  | SWS_Can_91017 | SWS_Can_91016 |  |  |  |  | E_NOT_OK |  | - | Deferred - Low (OP-B05a-13)
Can_GetControllerRxErrorCounter | 0x30 | SWS_Can_00514 |  |  | SWS_Can_00513 | SWS_Can_00512 |  |  |  |  | E_NOT_OK |  | - | Deferred - Low (OP-B05a-13)
Can_GetControllerTxErrorCounter | 0x31 | SWS_Can_00519 |  |  | SWS_Can_00518 | SWS_Can_00517 |  |  |  |  | E_NOT_OK |  | - | Deferred - Low (OP-B05a-13)
Can_GetCurrentTime (DRAFT) | 0x32 | SWS_Can_00523 |  |  | SWS_Can_00522 | SWS_Can_00521 |  |  |  |  | E_NOT_OK (00089) | CanGlobalTimeSupport | - | Deferred - Low (OP-B05a-13)
Can_EnableEgressTimeStamp (DRAFT) | 0x33 |  | SWS_Can_00526 |  |  | SWS_Can_00525 |  |  |  |  | None (void) | CanGlobalTimeSupport | - | Deferred - Low (OP-B05a-13)
Can_GetEgressTimeStamp (DRAFT) | 0x34 | SWS_Can_00532 | SWS_Can_00531 |  |  | SWS_Can_00529 |  |  |  | SWS_Can_00530 | E_NOT_OK | CanGlobalTimeSupport | - | Deferred - Low (OP-B05a-13)
Can_GetIngressTimeStamp (DRAFT) | 0x35 | SWS_Can_00537 | SWS_Can_00536 |  |  | SWS_Can_00535 |  |  |  |  | E_NOT_OK | CanGlobalTimeSupport | - | Deferred - Low (OP-B05a-13)
Can_Write | 0x06 | SWS_Can_00219 SWS_Can_00505 | SWS_Can_00217 | SWS_Can_00218 |  | SWS_Can_00216 |  |  |  |  | E_NOT_OK |  | 500; 501; 506; 507; 508 | In scope - Critical
Can_MainFunction_Write | 0x01 | [11 empty] | - | N/A (no DET requirement)
Can_MainFunction_Read | 0x08 | [11 empty] | - | N/A (no DET requirement)
Can_MainFunction_BusOff | 0x09 | [11 empty] | - | N/A (no DET requirement)
Can_MainFunction_Wakeup | 0x0A | [11 empty] | - | N/A (no DET requirement)
Can_MainFunction_Mode | 0x0C | [11 empty] | - | N/A (no DET requirement)
Number of APIs with this check |  | 9 | 4 | 1 | 10 | 14 | 3 | 1 | 0 | 1
CAN_E_INIT_FAILED = 0 APIs: defined in SWS_Can_91019 but not raised by any R24-11 API requirement (OP-B05a-06).
Scope: B05a SRS rows cover Can_Init, Can_DeInit, Can_SetControllerMode and Can_Write (9-SRS budget). Can_SetBaudrate DET checks are owned by B04a. Other APIs are kept here as the full R24-11 reference and listed as deferred in OP-B05a-13.

## Review Checklist
CAN Driver SRS Review Checklist and Log
Checklist ID | Review criterion | Pass condition | Category
CHK-01 | Requirement uses a mandatory shall-statement. | One obligation per requirement. | Wording
CHK-02 | Actor is explicitly the CAN Driver or a defined interface. | No implicit actor. | Clarity
CHK-03 | Trigger and preconditions are stated. | Behavior can be reproduced for verification. | Testability
CHK-04 | Expected behavior is measurable and unambiguous. | No vague terms such as appropriate, fast or normally. | Testability
CHK-05 | Exact AUTOSAR SWS source ID is recorded. | Every applicable SRS item has backward traceability. | Traceability
CHK-06 | Non-applicable SWS requirement has justification. | No silent exclusion. | Coverage
CHK-07 | DET, runtime error and return behavior are separated. | Error type and reaction are correct. | Error Handling
CHK-08 | No CanIf, CanSM, CanTp or Transceiver responsibility is assigned to CAN Driver. | Module boundary is preserved. | Architecture
CHK-09 | Configuration-dependent behavior is marked. | Pre-compile/link-time/post-build dependency is recorded where relevant. | Configuration
CHK-10 | Requirement is not duplicated or conflicting. | Single consistent behavior across the SRS. | Consistency